## Deploy Steps
Attachment Reader — Production Deploy Runbook
Generated: 2026-09-03 05:02 UTC
# | Phase | Action | Command / Details | Est. Time | Notes
1 | 0. Prerequisites | Check Forge CLI is current | forge --version (update: npm install -g @forge/cli@latest) | 2 min
2 | 0. Prerequisites | Confirm logged-in account has contributor access | forge whoami | 2 min | Wrong account is the most common cause of step 4 failures
3 | 1. Confirm target app | Check App ID in Developer Console matches manifest.yml | Console → org → app → App details → App ID | 3 min | Different orgs can each have their own registration of this code
4 | 1. Confirm target app | Sanity-check CLI can see the app | forge environments list / forge install list | 2 min | Must succeed before proceeding — auth error means wrong app ID or wrong account
5 | 2. Pre-flight | Lint the app | forge lint | 1 min | Fix any findings before deploying
6 | 2. Pre-flight | Sync dependencies | npm install | 2 min | Ensures node_modules matches package-lock.json
7 | 3. Deploy | Deploy to development | forge deploy -e development | 2 min
8 | 3. Deploy | Smoke test on development | Exercise the agent/action against a real issue | 10 min | Whatever site already has development installed
9 | 3. Deploy | Deploy to staging | forge deploy -e staging | 2 min
10 | 3. Deploy | Smoke test on staging | Exercise the agent/action against a real issue | 10 min
11 | 3. Deploy | Deploy to production | forge deploy -e production | 2 min | Only after dev + staging both pass
12 | 4. Install | Install or upgrade on target site (admin) | forge install -e production -s <site> -p Jira --confirm-scopes (add --upgrade for an existing install) | 3 min | Use the "you have admin" path
13 | 4. Install | Install on target site (no admin) | Share the distribution link from the Developer Console with a site admin | Depends on admin | developer.atlassian.com/console/myapps/<app-id>/distribution
14 | 5. Verify | Functional test every attachment type | PDF, DOCX, XLSX, TXT/CSV/JSON/Markdown, PNG/JPEG (OCR) | 15 min | Image OCR is the highest-risk path — see Known Risks tab
15 | 5. Verify | Check logs for errors | forge logs -e production -s <site> -g | 5 min
16 | 5. Verify | Roll back if needed | forge deploy list --json → forge deploy -e production -t <tag> | 5 min | Redeploys old code only; does not touch data
|  |  | Estimated active hands-on time (excludes admin wait) | ~66 min

## Known Risks
Known Risks
Risk | Detail | Mitigation
Image OCR — confirmed working (2026-09-03) | Correctly OCR'd a PNG screenshot on a live issue in a real Forge deploy. Was a real risk going in: tesseract.js's Node build spawns a worker_threads.Worker at a separate file path and loads its WASM engine via a runtime fs.readFileSync() — both reached dynamically, not through Forge's static single-file bundle graph. Evidently bundles/runs fine in practice. | Spot-check an image attachment after deploying to each new app registration or environment (bundler/runtime specifics could differ across accounts or future CLI versions); check forge logs for worker/WASM load failures if one ever comes back empty.
Image size / OCR timeout | Images are capped at 3MB (vs 5MB for other types) and OCR runs inside Forge’s ~25s function timeout. | Keep test images small; a dense/large image can still time out even under the cap.
Legacy .xls not supported | Only modern .xlsx is read (via exceljs) — legacy binary Excel (.xls, application/vnd.ms-excel) is not. | Ask users to re-save as .xlsx, or add a legacy-format library if this becomes a real need.
Read-only scope | The app only requests read:jira-work. | It cannot write back to issues — no scope changes needed for this deploy.